## Testing
Product Name | https://demowebshop.tricentis.com/ | TC Start Date | 2024-12-18 | TC Execution Start Date | 2024-12-18 |  |  |  |  | TEST CASES
Module Name |  | TC End Date | 2024-12-22 | TC Execution End Date | 2024-12-22 |  |  |  |  | PASS | 0
Epic |  | Test Case Devloped By | Abhishek Maurya | Browser (tested) | yes |  |  |  |  | FAIL | 0
Developer Name (TL) |  | Test Case Reviewed By | Vaishanavi | [6 empty] | Not Executed | 0
Test Executed by | [9 empty] | Out of Scope | 0
[10 empty] | TOTAL | 0
Test Case Id | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen shot | Final Staus | Remarks
TC001 | User Registration | Functional Testing | Creat Account | Verify registration with valid inputs | Account created successfully | Account successfully created, redirected to dashbo | Name: Abhishek Maurya, Email: mauryaabhi@gmail.com, Password: Abc@123 | 1. Go to the website. 2. Click on "Register." 3. Fill all fields with valid data. 4. Click "Register." | None | PASS
TC002 | User Registration | Usability Testing | Create Account | Verify error messages for invalid email | Error message displayed for invalid email | Error message: "Invalid email address" displayed under the email field | Name: Sbhidhrk, Email: giljklsfkfjd, Password: Abc@123 | 1. Go to the website. 2. Click on "Register." 3. Enter invalid email format in the email field. 4. Click "Register." | None | PASS
TC003 | Checkout | N0n-functional Testing | Checkout Process | Test load time for checkout page | Checkout page loads within 3 seconds | Page takes more than 5 seconds to load |  | None | None | FAIL
TC004 | Login | Functional | Login Functionality | Test login with valid credentials | User logs in successfully with correct credentials | User successfully logged in | Username: user1, Password: password123 | 1. Go to login page 2. Enter valid credentials 3. Click login | None | PASS
TC005 | Search | Non-Functional | Search Function | Test search performance with multiple results | Search results are displayed within 2 seconds | Search results take longer than expected | Search term: "Laptop | 1. Go to search bar 2. Type "Laptop" 3. Observe results | None | Blocked
TC006 | Registration | Functional | User Registration | Test mandatory field validation (empty fields) | Error message prompts the user to fill mandatory fields | Error message displayed for missing required fields | None | 1. Go to the registration page 2. Leave required fields empty 3. Submit | None | PASS
TC007 | Login | Functional | Login Functionality | Test login with incorrect password | Item 1: Laptop, Item 2: Phone | Error message displayed for incorrect password | Username: user1, Password: wrongpassword | 1. Go to login page 2. Enter incorrect password 3. Click login | None | PASS
TC008 | Checkout | Functional | Checkout Process | Test applying discount code | Discount is applied correctly if the code is valid | Discount applied correctly | Discount code: SAVE10 | 1. Go to checkout page 2. Enter discount code 3. Apply | None | PASS
TC009 | Product Page | Functional | Product Availabilit | Test product availability (in-stock items) | Product availability status is displayed as "In Stock" or "Out of Stock" | Product is correctly marked as in-stock or out-of-stock | None | 1. Go to product page 2. Observe availability status | None | PASS
TC010 | Cart | Functional | Shopping Cart | Test adding multiple items to the shopping cart | All added items appear in the cart | All added items appear in the cart | Item 1: Laptop, Item 2: Phone | 1. Add items to cart 2. Go to shopping cart 3. Check if all items appear | None | PASS
TC011 | Order | Functional | Order Confirmation | Test order confirmation page after successful order placement | The order confirmation page displays correct order detail | Correct order details displayed | None | 1. Complete the checkout process 2. View order confirmation | None | PASS
TC012 | Login | Non-Functional | Load Testing | Test system's response time when multiple users log in simultaneously | The system responds within 2 seconds even under high load | The system took longer than expected to respond | 1000 virtual users | 1. Simulate login for multiple users at the same time | None | FAIL
TC013 | Checkout | Non-Functional | Stress Testing | Test system performance with a large number of items in the cart | System processes orders without crashing or slowing down | System became unresponsive with a large number of items | 1000 items | 1. Add a large number of items to the cart 2. Try checking out | None | FaIL
TC014 | All Modules | Non-Functional | Usability Testing | Test website usability on mobile devices | The website is fully functional and user-friendly on mobile devices | Some buttons are not clickable on mobile | None | 1. Open website on mobile 2. Check functionality of button | None | FAIL
TC015 | All Modules | Non-Functiona | Compatibility Testing | Test website compatibility across different browsers (Chrome, Firefox, Safari) | Website works properly across all browser | Minor layout issues found in Safari | None | 1. Open website in Chrome, Firefox, and Safari 2. Compare functionalit | Screenshot of issue | FAIL
TC016 | Cart | Non-Functional | Security Testing | Test SQL injection vulnerability in the cart page | No data can be inserted or modified via SQL injection | SQL injection was successful | None | 1. Try to input SQL command in the cart URL 2. Observe behavior | Screenshot of issue | FAIL
TC017 | UI | Ui testing | Layout | Verify if the page layout is responsive on desktop. | The layout should be consistent and responsive on desktop | The layout consistent and reponsive on desktop | Desktop,Laptop | 1.Open website on a desktop. | None | PASS
TC018 | UI | Ui testing | Layout | Verify if the page layout is responsive on tablet and phone | The layout should be consistent and responsive on tablet and phone | The layout consistent and reponsive on tablet and phone | Tab and Phone | 1.Open website on a Tab and Phone. | None | PASS
TC019 | UI | Ui testing | Error Message Check | Verify if error message are displayed correctly | Invalid email.Worng Password | Clear and User-Friendly error message should appear. | None | 1.Enter invalid data in the from. 2.Submit the from. 3.Verify error message | None | PASS
TC020 | Footer | Usability Testing | Error Handling | Verify if the page handling is user-friendly | Error message should be clear and helpful with guidance for user. | Error Message is clear and helpful with guidance for user | Error scenario(e.g-Worng URL) | 1.Trigger an error(e.g-404). 2.Check the error message and resolution instructions. | None | PASS